## Sheet1
Date: | 2017-02-19 | 2017-02-26 | 2017-03-05 | 2017-03-12 | 2017-03-19 | 2017-03-26 | 2017-04-02 | 2017-04-09 | 2017-04-16 | 2017-04-23 | 2017-04-30 | 2017-05-07 | 2017-05-14 | 2017-05-21 | 2017-05-28 | 2017-06-04 | 06/11/207 | 2017-06-18 | 2017-06-25 | 2017-07-02 | 2017-07-09 | 2017-07-16 | 2017-07-23 | 2017-07-30 | Totals
Objectives: | Complete Initial Schedule | Continue work on prototype | Complete prototype, work on Design Documents. Initial prototype demo to single stakeholder | Update Design Documents based on prototype | Update Design Documents based on prototype | Demo prototype GUI again | Update Design Documents based on prototype | Demo Final Prototype to Stakeholders | Start final Design on GUI. Update requirements based on user feedback | Start final Design on GUI. Update requirements based on user feedback | Work on final Design Documents and final set of requirements | Between semesters | Continue work on final Design Documents. Start full implementation of business logic | Continue work on final Design Documents | Start implementation stage | Continue implementation | Continue implementation. Work on user guide documentation | Continue implementation. Work on user guide documentation | Continue implementation. Work on user guide documentation | Continue implementation. Work on user guide documentation | Finish final product | Deploy Product. Review documentation with store managers, update documentation when neccesary | Review documentation with store managers, update documentation when neccesary | List project lessons learned
Deliverables: | Schedule version 1 Budget Estimates version 1 | Latest version of prototype (including source code and Design Documents Refined Schedule Progress Report 1 Weekly Status | Latest version of prototype (including source code and Design Documents Refined Schedule Weekly Status | Latest version of prototype (including source code and Design Documents Refined Schedule Weekly Status | Latest version of prototype (including source code and Design Documents Refined Schedule Weekly Status | Latest version of prototype (including source code and Design Documents Refined Schedule Progress Report 2 Weekly Status | Latest version of prototype (including source code and Design Documents Weekly Status | Latest version of prototype (including source code and Design Documents. Stakeholder Meeting documentation | Design Documents Weekly Status | Design Documents Weekly Status | Final summer Design Documents | N/A | Design Documents Source Code Update Schedule (if due dates change) | Design Documents Source Code | Design Documents Source Code Test Cases User Feedback | Design Documents Source Code Test Cases User Feedback | Design Documents Source Code Test Cases User Feedback | Design Documents Source Code Test Cases User Feedback | Design Documents Source Code Test Cases User Feedback | Design Documents Source Code Test Cases User Feedback | Final Source Code, Design Documents and Test Cases | User Feedback Code Updates (if needed) | User Feedback Code Updates (if needed)
Important Dates: |  | (2/24) Demo prototype with stakeholder (John) | 3/11 Phone Demo prototype with stakeholder (John) | Spring Break Mar 13-17 |  |  |  | Previous demo date, moved a month for more review from client due to issues having in person meetings | Client Meeting on 4/14/2017 |  | Last week of summer semester | [9 empty] | Demo with 4 District Managers and Company Vice President. In Geneva, AL | Test program installs at Stores |  | Final week
Sprint Number: Primary Focus in ()'s | Sprint 1 (Initial Design, Requirements Gathering) |  |  | Sprint 2 (Requirements Refining, Prototype) |  |  | Sprint 3 (Prototype) |  | Sprint 4 (Requirements Completion, Design) |  |  | BREAK | Sprint 5 (Design) |  | Sprint 6 (Design, Some Implementation and Testing) |  |  | Sprint 7 (Implementation/Testing) |  | Sprint 8 (Implementation/Testing) |  | Sprint 9 (Testing/Documentation)
Estimated Hours For Engineer | N/A | 8 | 8 | 3 | 10 | 10 | 15 | 12 (Revised) | 15 | 10 | 8 | 6 (Revised) | 12 | 10 | 11 | 8 | 8 | 15 | 8 | 12 | 10 | 15 | 8 | 15 | 219
Actual Hours Worked | N/A | 10 | 6 | 3 | 12 | 12 | 6 | 8 | 10 | 10 | 6 | 6 | 14 | 7 | 8 | 8 | 6 | 15 | 12 | 14 | 10 | 8 |  |  | 191